## Org
Project-Plan
Group 08 - Section 02 - global
Team-Members | USA | USA | USA | USA | Germany | Germany | Germany | Germany | Germany
Team_ID | TL | M2 | M3 | M4
First Name | Falco | Richard | Karan | Vidit Joy
Last Name | Becker | Robinson | Grupta | Manglan
Position | Team Lead | Member 2 | Member 3 | Member 4
phone | +1 (415) 319-4613
mail | falcobecker@freenet.de
shell | fbecker
knowledge

## M0
Milestone Deadline: |  | M0
Deadline: |  | 09/25/2017 - 23:59
Member | M_ID | Tasks | Task-Deadline: | estimated finish-date: | Done | InProgress | Issue | Description
testMember | t_id | test task, which is done |  |  | x
|  | test task, which is in progress |  |  |  | x |  | i will be in time
|  | test task, which is critical |  |  |  |  | x | need help, have not the knowledge
Falco Becker | TL | creating organisation documents | 09/25/2017 | 09/24/2017 | x |  |  | "i was one day late"
| TL | upload everything and write the email that M0 is finished | 09/25/2017 | 09/25/2017 |  | x | x | waiting for finnishing the technical part of M0
"rest of the team" | M2 | finishing the technical part of M0 | 09/25/2017 | 09/25/2017 |  | x
M3
M4
| M2 | creating shell and mysql account | 09/25/2017 | 09/25/2017 | x
| M2 | download and install webstorm | 09/25/2017 |  |  | x
| M3 | creating shell and mysql account | 09/25/2017 | 09/25/2017 | x
| M3 | download and install webstorm | 09/25/2017 |  |  | x
| M4 | creating shell and mysql account | 09/25/2017 | 09/25/2017 | x
| M4 | download and install webstorm | 09/25/2017 |  |  | x
everybody | MA | Faster Task: get fucked by project!
[5 empty] | x | x | x

## M1
Milestone Deadline: |  | M1
Deadline: |  | 09/25/2017 - 23:59
Member | M_ID | Tasks | Task-Deadline: | estimated finish-date: | Done | InProgress | Issue | Description
testMember | t_id | test task, which is done |  |  | x
|  | test task, which is in progress |  |  |  | x |  | i will be in time
|  | test task, which is critical |  |  |  |  | x | need help, have not the knowledge
[5 empty] | x | x | x

## M2
Milestone Deadline: |  | M2
Deadline: |  | 09/25/2017 - 23:59
Member | M_ID | Tasks | Task-Deadline: | estimated finish-date: | Done | InProgress | Issue | Description
testMember | t_id | test task, which is done |  |  | x
|  | test task, which is in progress |  |  |  | x |  | i will be in time
|  | test task, which is critical |  |  |  |  | x | need help, have not the knowledge
[5 empty] | x | x | x